## PMP
Review No. | Raised By | Issue Date | Issue | Status | Approved By | Closed date
PMP_1 | Marina Hatem | 13.4.2022 | In 3.1, please provide the specific section of Quality Control you are follwing in ISTQB | Open
PMP_2 | Marina Hatem | 13.4.2022 | Please provide the project name at the top of all pages. | Open
PMP_3 | Marina Hatem | 13.4.2022 | Please provide a definition for the following terms in Appendix C: "Dark Data" , "Email Bounce" , "Gap Analysis", "" | Open
PMP_4 | Marina Hatem | 13.4.2022 | In section 3.3, There are clear copied text. For example: "Set your quality standards. Decide which quality standards to focus on. . Get feedback." Please adjust it. | Open
PMP_5 | Marina Hatem | 13.4.2022 | Please remove the unnecessary blue text in all the sheet. | Open
PMP_6 | Marina Hatem | 13.4.2022 | Please provide a definition for the ISTQB in Appendix B | Open

## Options (hidden)
Open
Close

## SRS
Review No. | Raised By | Issue Date | Issue | Status | Approved By | Closed date
1 | Hager Hany | 2022-04-13 | in section 3.11.3 field constrantions the last one must be phone number not full name | Open
2 | Hager Hany | 2022-04-13 | there is a missing admin function which is update user | Open
3 | Hager Hany | 2022-04-13 | there is a issue in the numbering starts from 3.15 subtitles till the end of the section 3 | Open
4 | Hager Hany | 2022-04-13 | there is a issue in 3.16 in functional requirments it doesn't match the actual requirment fo adding an admin | Open
5 | Hager Hany | 2022-04-13 | the usage of the admin and user keywords interchangably is not applicable so please revise the functionality of the adim as whole | Open
6 | Hager Hany | 2022-04-13 | the add item /delete /update item is not in our scope | Open
7 | Hager Hany | 2022-04-13 | section 3.22 has a conflict topic | Open
8 | Hager Hany | 2022-04-13 | missing admin function which is update add delete menu | Open
9 | Hager Hany | 2022-04-13 | in section 5.3 the authorization some functions of admin is forgotten which is add/update/delet menus | Open
10 | Hager Hany | 2022-04-13 | in section 5.1 I think we need to remove the part of the delay of 5 seconds | Open
11 | Hager Hany | 2022-04-13 | in section 5.4 we need to express the avialibilty in nines we can review this link to help https://www.blameless.com/sre/availability-maintainability-reliability-whats-the-difference | Open
12 | Hagar EL-Sayed | 2022-04-13 | in the first page the prepared by section font and arrage of the members names is not right | Open
13 | Hagar EL-Sayed | 2022-04-13 | in section 1.1, the Purpose there is a problem in the sequence espcially here "The customers can get their order delivered" and then the rest | Open
14 | Hagar EL-Sayed | 2022-04-14 | in section 1.2 there is a problem in the word content it is written "containt" | Open
15 | Hagar EL-Sayed | 2022-04-14 | in section 1.2 , it is better to mention that changing the content is called "tailoring" | Open
16 | Hagar EL-Sayed | 2022-04-14 | in section 1.3 nonfunctional requirements is written "nonfunction" | Open
17 | Hagar EL-Sayed | 2022-04-15 | in section 1.4 the sentence is not written right " after choose" we recommend "After choosing" | Open
18 | Hagar EL-Sayed | 2022-04-15 | in section 1.4 the last sentence "based on ….." it needs declaration. | Open
19 | Hagar EL-Sayed | 2022-04-15 | in section 2.1 "Web app file-based" we recommend using the term "Web-based application" | Open
20 | Hagar EL-Sayed | 2022-04-15 | in section 2.3 we recommend using Javascript instead of "js" | Open
21 | Hagar EL-Sayed | 2022-04-15 | in section 2.5 it is recommended to specify how the system is going to know the near by restaurants is it by using the GPS or the user insert the required place or any other methods | Open
23 | Hagar EL-Sayed | 2022-04-15 | in section 3.2 there is a missing error message if the user insert a wrong data | Open
24 | Hagar EL-Sayed | 2022-04-15 | in section 3.6 there are missing steps what happen after the user "view the restaurant’s menu" | Open
25 | Hagar EL-Sayed | 2022-04-15 | in section 3.6.3, REQ-2 the user has to select the restaurant to" View their menu then choose te meal". | Open

## Progress_Chart
PMP | Open | 6 | SRS | Open | 24
| Closed | 0 |  | Closed | 0
| Total | 6 |  | Total | 24