## SIQ_Ass_Foodies
Organization: |  | ITI-QA-42
Document: |  | SIQ/Assumptions
Group No: |  | E
Project Name: |  | Foodies
No. | Question Date | Who Asked | Question | Answer | Date of Answer | Who Answered | Status
SIQ-1 | 9.4.2022 | Nora | Does the User need to add His location during registration so that accordingly the nearby restaurants are displayed? | Location is entered in Registration. | 9.4.2022 | Amr | Closed
SIQ-2 | 9.4.2022 | Hager Hany | What exactly are the admin features? ADD/DELETE/UPDATE users, restaurants, menus and promotions.? | ADD/DELETE/UPDATE users restaurants, menus, promotions and can also add admins. | 9.4.2022 | Amr | Closed
SIQ-3 | 9.4.2022 | Aml | Do we need Database in development or not? For (Emails, Passwords and user IDs) | We can use file based. | 9.4.2022 | Amr | Closed
SIQ-4 | 9.4.2022 | Marina | The exact Registration fields are email and password, Right? | The registration form fields are: Email, Password, User ID, Phone Number, Location. | 9.4.2022 | Amr | Closed
SIQ-5 | 9.4.2022 | Nora | Will the offers page and Loyalty Points page be joined or separated? | Offers page and Loyalty Points can be in one page. | 9.4.2022 | Amr | Closed
SIQ-6 | 9.4.2022 | Hager Hany | The payment method is Cash on Delivery only, Right? | Cash On Delivery is the only payment method. | 9.4.2022 | Amr | Closed
SIQ-7 | 9.4.2022 | Aml | What do you mean by 'Different services' in the description when you stated that "Also the restaurant owner can promote their menus and different services"? | Only restaurants' Menus and promotions can added. | 9.4.2022 | Amr | Closed
No. | Question Date | Who Assume | Assumption | Answer | Date of Answer | Who Answered | Status
Ass-1 | 9.4.2022 | Marina | We need a Login / Log out / tracting Order / Pages | Agreed On Login/tracting Order Pages | 9.4.2022 | Amr | Closed