## week-two-detailed-tim
Week two detailed time plan
Detailed description for week two tasks and their progress. | Link : https://hagar-nassar.monday.com/boards/2580117308
Main Tasks
Name | Person | Status | Timeline - Start | Timeline - End
ERD | Aml-Nasser | Done | 2022-04-16 | 2022-04-20
Sequence | Hanyhager120@gmail.com, Marina Hatem Habib | Done | 2022-04-16 | 2022-04-20
Wireframe | Hagar Nassar | Done | 2022-04-16 | 2022-04-20
Usecase | namr7333@gmail.com | Done | 2022-04-16 | 2022-04-20
|  |  | 2022-04-16 | 2022-04-20
Review Tasks
Name | Person | Status | Timeline - Start | Timeline - End
Review ERD | Marina Hatem Habib | Done | 2022-04-20 | 2022-04-22
Review Sequence | Hagar Nassar | Done | 2022-04-20 | 2022-04-22
Review Wireframe | Aml-Nasser | Done | 2022-04-20 | 2022-04-22
Review Usecase | Hanyhager120@gmail.com | Done | 2022-04-20 | 2022-04-22
|  |  | 2022-04-20 | 2022-04-22