## week-one-detailed-tim
Week one detailed time plan
Week One detailed time plan for task and task progress management | Time plan link: https://hagar-nassar.monday.com/boards/2536007828
Main tasks
Name | Person | Status | Timeline - Start | Timeline - End | Progress Tracking
SIQ | Hagar Nassar, namr7333@gmail.com, Hanyhager120@gmail.com, Marina Hatem Habib | Done | 2022-04-09 | 2022-04-12 | 100%
Creating Time plan | Hagar Nassar | Done | 2022-04-09 | 2022-04-15 | 100%
Creating SRS | Marina Hatem Habib, namr7333@gmail.com | Done | 2022-04-11 | 2022-04-15 | 100%
Creating PMP | Hanyhager120@gmail.com, Aml-Nasser | Done | 2022-04-09 | 2022-04-14 | 100%
Creating Github | Aml-Nasser | Done | 2022-04-09 | 2022-04-12 | 100%
Creating quality management plan | Hagar Nassar, namr7333@gmail.com | Done | 2022-04-11 | 2022-04-13 | 100%
|  |  | 2022-04-09 | 2022-04-15 | 100%
Review tasks
Name | Person | Status | Timeline - Start | Timeline - End | Progress Tracking
Review SIQ | Hagar Nassar, Aml-Nasser, Hanyhager120@gmail.com, namr7333@gmail.com, Marina Hatem Habib | Done | 2022-04-13 | 2022-04-15 | 100%
Review time plan | Aml-Nasser | Done | 2022-04-13 | 2022-04-15 | 100%
Review SRS | Hagar Nassar, Hanyhager120@gmail.com | Done | 2022-04-13 | 2022-04-15 | 100%
Review PMP | Marina Hatem Habib, namr7333@gmail.com | Done | 2022-04-13 | 2022-04-15 | 100%
Review quality management plan | Hanyhager120@gmail.com, Marina Hatem Habib | Done | 2022-04-13 | 2022-04-15 | 100%
|  |  | 2022-04-13 | 2022-04-15 | 100%